## Bryan_Burndown_Data
Time Period | Ideal Remaining Work | Actual Remaining Work
Sprint 6 Start | 30 | 30
End of Sprint 6 | 15 | 20
Mid Sprint 7 | 5 | 7
End of Sprint 7 | 0 | 0

## Bryan_Sprint_Tasks
Task ID | Description | Servlet/Component | Primary Sprint | Work Units
T1 | Login handling (auth / session start) | LoginServlet.java | Sprint 6–7 | 2
T2 | Logout handling (session end) | LogoutServlet.java | Sprint 6–7 | 2
T3 | User registration flow | RegistrationServlet.java | Sprint 6–7 | 2
T4 | Main user dashboard routing/data prep | DashboardServlet.java | Sprint 6–7 | 2
T5 | Calendar event data endpoint (simulated) | CalendarDataServlet.java | Sprint 6–7 | 2
T6 | Chart/progress data endpoint (simulated) | ChartDataServlet.java | Sprint 6–7 | 2
T7 | Workout logging entry handling | LogWorkoutServlet.java | Sprint 6–7 | 2
T8 | Process workout log submission (POST handling) | ProcessLogWorkoutServlet.java | Sprint 6–7 | 2
T9 | View workout session details | ViewSessionServlet.java | Sprint 6–7 | 2
T10 | View workout plan details | PlanDetailsServlet.java | Sprint 6–7 | 2
T11 | Update workout plan handling | UpdatePlanServlet.java | Sprint 6–7 | 2
T12 | Toggle plan status (activate/deactivate) | TogglePlanStatusServlet.java | Sprint 7 | 2
T13 | Google Fit integration toggle (simulated) | GoogleFitToggleServlet.java | Sprint 7 | 2
T14 | Apple Health integration toggle (simulated) | AppleHealthToggleServlet.java | Sprint 7 | 2
T15 | Auth/session cache/filter protection | AuthCacheFilter.java | Sprint 6–7 | 2

## Notes
Suggested caption (paste under chart):
Sprint 6 focused on implementing and wiring core backend endpoints. Sprint 7 focused on debugging, integration, and final fixes leading into the demo.